## Risk Registry
# | Rank | Name | Description | Category | Type | Root cause | Trigger | Risk Owner | Probability | Impact | Status
R1 | 1 | Security threat | Cyber attacks, hacking may lead to the disfunctioning of the platform | Technology | Negative | Poor security requirement collection and set-up | Attackers' interest on IT infrastructure, client lists, financial details of business | Sabina | 9 | 8 | Open
R2 | 2 | User feedback | Getting feedbacks from users may assist on developing varied customer segmentation techniques | Other | Positive | Modelling business strategies based on user preferences | Product improvement, understanding users, obtaining testimonials and reviews | James, Richard | 4 | 10 | Waiting
R3 | 4 | User privacy | Personal data breach (financial details, login credentials) may result decline in the platform reputation and user list | Technology | Negative | Poor security requirement collection and set-up | Cyber attack(s) | Sabina | 3 | 10 | In progress
R4 | 1 | Advertisement | Advertisement of the platform over social media may both increase the sales rate and push other people to raise awareness on wastefulness | Other | Positive | Willing to get more sales and interaction from/with target audience | Driving targeted traffic to the platform, rapidly increasing ROI rate on social media ads, gaining insights into users | Emma | 10 | 3 | In progress
R5 | 4 | Budget overrun | Spending more than estimated amount of money to complete the project | Financial | Negative | Inaccurate OPEX/CAPEX planning | Deviating from design decisions, estimation errors in high-level requirements, schedule extension/compression, inefficient stakeholder communication | Sabina | 3 | 10 | Open
R6 | 3 | Platform | Professionally designed platform with optimized backend processing may distinguish the business from competitors | Technology | Positive | Consistently achieving set business/financial goals | Platform performance, design, eager to improve fame and user acquisition | Mike, Charlie | 9 | 7 | In progress
R7 | 5 | Time excess | Delay in the fulfillment of WBS tasks may jeopardize to meet the delivery date | Other | Negative | Weak OPA/EEF consideration, insufficient work done by team members | Deviating from design decisions, estimation errors in high-level requirements, schedule extension, inefficient stakeholder communication, health issues | Sabina | 3 | 9 | Open
R8 | 4 | Monthly discounts | Offering monthly discounts on certain products under the control of owner | Financial | Positive | Engaging sellers into business at an optimum time to increase sales | Boosting CLV, analyzing post-purchase user behavior | James, Finn | 2 | 6 | Open
R9 | 7 | SEO measures | SEO measures may have rapid change anytime in which considerable drop in platform traffic and financial loss may be observed | Technology | Negative | Changed SEO measures to the search queries that are compatible with the content of the platform | Accessability failure to content by SE, change in hierarchical structure of platform, giving irrelevant keywords (combinations) for search queries, lack of backlinks - trustworthiness | System admin | 2 | 8 | Open
R10 | 4 | Return/Refund policy | Having smooth and trusted return/refund policy may let customers to carry out confident shopping | Other | Positive | Willing to observe an enhancement in the user satisfaction and user list | Changed buyer mind, late shipping, putting return/refund procedure into action upon buyer request | Altun, James | 4 | 3 | Open
R11 | 3 | System failure | Unexpected system failures may lead to downtimes, crashes, as a result, customer disputes | Technology | Negative | Lack of precaution in development and post-delivery | Code errors, traffic overloads - DDoS attacks, PaaS and DNS provider downtime, hosting expiration | System admin, Mike, Charlie and Özgür | 7 | 9 | In progress
R12 | 2 | Database failure | Loss of non-volatile memory/data | Technology | Negative | Sync backup mechanism | Unsolved configuration bugs, system crash, user errors, sabotage to data, hardware or software facilities, network/power failure, natural disasters | Sabina | 7 | 10 | In progress
R13 | 6 | Shipping delay | Exceeding the previously defined period may result in customer dissatisfaction | Other | Negative | İrresponsibility of transport service | Lack of available shipping vehicles | I - Bernard; II - Sabina, Altun | 5 | 5 | Open
R14 | 8 | USD rate | Increment in USD rate | Financial | Negative | Economic activity and outlook of US | Higher interest rates, political and economic stability and the demand for US goods and services | Finn | 3 | 3 | Open

## Sheet1
# | Rank | Name | Description | Category | Type | Root cause | Trigger | Risk Owner | Probability | Impact | Status
R6 | 1 | Platform | Professionally designed platform with optimized backend processing may distinguish the business from competitors | Technology | Positive | Consistently achieving set business/financial goals | Platform performance, design, eager to improve fame and user acquisition | Mike, Charlie | 9 | 7 | In progress
R2 | 2 | User feedback | Getting feedbacks from users may assist on developing varied customer segmentation techniques | Other | Positive | Modelling business strategies based on user preferences | Product improvement, understanding users, obtaining testimonials and reviews | James, Richard | 4 | 10 | Waiting
R4 | 3 | Advertisement | Advertisement of the platform over social media may both increase the sales rate and push other people to raise awareness on wastefulness | Other | Positive | Willing to get more sales and interaction from/with target audience | Driving targeted traffic to the platform, rapidly increasing ROI rate on social media ads, gaining insights into users | Emma | 10 | 3 | In progress
R8 | 4 | Monthly discounts | Offering monthly discounts on certain products under the control of owner | Financial | Positive | Engaging sellers into business at an optimum time to increase sales | Boosting CLV, analyzing post-purchase user behavior | James, Finn | 2 | 6 | Open
R10 | 4 | Return/Refund policy | Having smooth and trusted return/refund policy may let customers to carry out confident shopping | Other | Positive | Willing to observe an enhancement in the user satisfaction and user list | Changed buyer mind, late shipping, putting return/refund procedure into action upon buyer request | Altun, James | 4 | 3 | Open
# | Rank | Name | Description | Category | Type | Root cause | Trigger | Risk Owner | Probability | Impact | Status
R1 | 1 | Security threat | Cyber attacks, hacking may lead to the disfunctioning of the platform | Technology | Negative | Poor security requirement collection and set-up | Attackers' interest on IT infrastructure, client lists, financial details of business | Sabina | 9 | 8 | Open
R12 | 2 | Database failure | Loss of non-volatile memory/data | Technology | Negative | Sync backup mechanism | Unsolved configuration bugs, system crash, user errors, sabotage to data, hardware or software facilities, network/power failure, natural disasters | Sabina | 7 | 10 | In progress
R11 | 3 | System failure | Unexpected system failures may lead to downtimes, crashes, as a result, customer disputes | Technology | Negative | Lack of precaution in development and post-delivery | Code errors, traffic overloads - DDoS attacks, PaaS and DNS provider downtime, hosting expiration | System admin, Mike, Charlie and Özgür | 7 | 9 | In progress
R3 | 4 | User privacy | Personal data breach (financial details, login credentials) may result decline in the platform reputation and user list | Technology | Negative | Poor security requirement collection and set-up | Cyber attack(s) | Sabina | 3 | 10 | In progress
R5 | 4 | Budget overrun | Spending more than estimated amount of money to complete the project | Financial | Negative | Inaccurate OPEX/CAPEX planning | Deviating from design decisions, estimation errors in high-level requirements, schedule extension/compression, inefficient stakeholder communication | Sabina | 3 | 10 | Open
R7 | 5 | Time excess | Delay in the fulfillment of WBS tasks may jeopardize to meet the delivery date | Other | Negative | Weak OPA/EEF consideration, insufficient work done by team members | Deviating from design decisions, estimation errors in high-level requirements, schedule extension, inefficient stakeholder communication, health issues | Sabina | 3 | 9 | Open
R13 | 6 | Shipping delay | Exceeding the previously defined period may result in customer dissatisfaction | Other | Negative | İrresponsibility of transport service | Lack of available shipping vehicles | I - Bernard; II - Sabina, Altun | 5 | 5 | Open
R9 | 7 | SEO measures | SEO measures may have rapid change anytime in which considerable drop in platform traffic and financial loss may be observed | Technology | Negative | Changed SEO measures to the search queries that are compatible with the content of the platform | Accessability failure to content by SE, change in hierarchical structure of platform, giving irrelevant keywords (combinations) for search queries, lack of backlinks - trustworthiness | System admin | 2 | 8 | Open
R14 | 8 | USD rate | Increment in USD rate | Financial | Negative | Economic activity and outlook of US | Higher interest rates, political and economic stability and the demand for US goods and services | Finn | 3 | 3 | Open
Positive Risks
Negative Risks

## P-I matrix I
# | Probability | Impact
R1 | 9 | 8
R3 | 3 | 10
R5 | 3 | 10
R7 | 3 | 9
R9 | 2 | 8
R11 | 7 | 9
R12 | 7 | 10
R13 | 5 | 5 | requires daily monitoring
R14 | 3 | 3 | requires weekly monitoring
requires monthly monitoring

## P-I matrix II
# | Probability | Impact
R2 | 4 | 10
R4 | 10 | 3
R6 | 9 | 7
R8 | 2 | 6
R10 | 4 | 3
requires daily monitoring
requires weekly monitoring
requires monthly monitoring

## Top 10 risks
# | Name | Probability | Impact | Score
R1 | Security threat | 9 | 8 | 72
R12 | Database failure | 7 | 10 | 70
R6 | Platform | 9 | 7 | 63
R11 | System failure | 7 | 9 | 63
R2 | User feedback | 4 | 10 | 40
R3 | User privacy | 3 | 10 | 30
R4 | Advertisement | 10 | 3 | 30
R5 | Budget overrun | 3 | 10 | 30
R7 | Time excess | 3 | 9 | 27
R13 | Shipping delay | 5 | 5 | 25